## DC
dc.citation.endPage | dc.citation.number | dc.citation.startPage | dc.citation.title | dc.citation.volume | dc.contributor.author | dc.date.issued | dc.description.abstract | dc.identifier.bibliographicCitation | dc.identifier.issn | dc.identifier.uri | dc.language.iso | dc.publisher | dc.subject.keyword | dc.title.alternative | dc.title | dc.type.other | dc.type
293 | 3 | 286 | 한국군사과학기술학회지 | 23 | 조정호¦¦ 임재성¦¦ | 2020-06 | Since Dr. Lipke announces earned schedule management(ESM) in 2002, it has been used in project management to make up for the insufficient schedule management function of earned value management technique. However, it is difficult to accurately forecast the schedule of delayed defense research and development(R&D) projects with the ESM technique. Therefore, this paper proposes a new schedule forecasting method considering the progress of delayed work in ESM technique. This concept can also be adopted to the traditional project progress management (PPM) technique. We verify the effectiveness of the proposed concept through several defense R&D projects and prove that it is possible to supplement the schedule forecasting of the ESM and PPM technique. | 한국군사과학기술학회지, Vol.23 No.3, pp.286-293 | 1598-9127 | https://aurora.ajou.ac.kr/handle/2018.oak/37444¦¦ https://www.kci.go.kr/kciportal/ci/sereArticleSearch/ciSereArtiView.kci?sereArticleSearchBean.artiId=ART002592687¦¦ | Kor | 한국군사과학기술학회 | Earned Schedule Management¦¦ Project Progress Management¦¦ Schedule Estimate at Completion¦¦ | Research on Improving Schedule Forecasting Method for Delayed Defense Research & Development Project | 지연된 국방 연구개발 프로젝트의 일정 예측방식 개선 연구 | Article | Article